## README
EINT MuleSoft Backlog Tracker — How This Works
Replaces: MuleSoft Team - Planning.xlsx and Requirements Traceability Matrix - EINT Mulesoft 2026.xlsx
The golden rule: every field has exactly one home.
Each requirement is one row, tracked by its Requirement ID across every tab below. Each field (Priority, Sprint, Dependencies, Release, etc.) is only ever typed into ONE tab — the tab owned by the role responsible for it. Every other tab shows that same field automatically, pulled live from wherever it was entered. If you change it in its home tab, it updates everywhere else immediately. Nobody should ever need to copy a value between tabs by hand.
Colour legend
Text is plain black everywhere. Row shading instead shows which Stream an item belongs to (applied automatically via conditional formatting, so it updates itself as Stream values change):
US
MyMSC
Rollout / MVP Rollout
Backlog / Growth
Tech Enhancements
PI11, PI12, or any other PI-specific stream
Cross, or any other stream not listed above -- no shading (white/default)
Who's allowed to edit which field is documented in the ownership table below, not by colour anymore.
Requirement ID convention
Use the Jira key (e.g. INT-171) as the Requirement ID whenever a Jira ticket already exists. Anyone can also add a future item straight to the Backlog tab with no Jira ticket at all — give it a temporary ID in the form NEW-0001, NEW-0002, etc. IMPORTANT: this Requirement ID never changes afterwards, even once a real Jira ticket exists for it — every other tab is joined to this ID, so swapping it would break those links. When the item is ready to become a real Jira ticket, set 'Create Jira Ticket?' to Yes on the Backlog tab; the returned Jira key is written into the separate Jira Key / Jira Link columns alongside the ID, not in place of it.
Tab ownership — who edits what
Tab | Owner | Types here (input) | Shown automatically (pulled)
Backlog | Anyone (entry point) | Requirement Name, Type, Stream, Status, Date Added, Create Jira Ticket?, Jira Key | Jira Link, Priority, Sprint, Release
API Design Planning | API Design Lead | RAML Required, RAML Delivery Date, Assignee, Priority, Design Status, Handover | Requirement Name, Stream, Jira Link, Status, Sprint
RTM | BA | Predecessor, Successor, Dependency Status, Notes | Requirement Name, Stream, Jira Link, Status, Priority, Sprint
Sprint Planning | BA / PO / SM | Sprint, HLE | Requirement Name, Stream, Priority, Status
Roadmap | Nobody — all view | (fully automatic) | Stream x Sprint HLE grid
Release | DM / SM | Release | Requirement Name, Stream, Sprint, Status, Priority, HLE
Status: template only
This workbook is currently a clean, empty structure — no data has been migrated yet. Automations planned for later phases are NOT yet wired up:
1. Jira (labelled ticket) -> auto-creates a Backlog row with Jira Key/Link filled in.
2. Any new Backlog row (Jira-sourced or typed straight in with no Jira ticket) -> auto-creates a Trello card.
3. Sprint changed for an item -> updates the sprint label on its Trello card.
4. 'Create Jira Ticket?' set to Yes on a manually-added row -> creates the Jira issue and writes the key back into Jira Key/Jira Link, then flips the flag to Created.
5. Scheduled refresh of the RTM Dependency Status column from the live status of the Predecessor/Successor Jira key.
Until these are wired up, fill in Jira Key, Predecessor/Successor, and Dependency Status manually.
Sprint Planning sort order
Sprint Planning is kept sorted ascending by Sprint (lowest in-scope sprint first, unassigned/'To Plan' last), using a hidden 'Sort Key' column (H) that converts the Sprint text to a number. If you add new rows and want to re-sort, select the table and use Data > Sort by column H — don't unhide/delete that column.
Release tab population
The Release tab lists every item that has a real Sprint assigned in Sprint Planning (not blank/'To Plan') — once an item gets a sprint for the first time, add its Requirement ID to the Release tab so DM/SM can assign it a Release. This mirrors how RTM/Sprint Planning/API Design Planning already work: copy the ID over when the item reaches that stage.
Quarterly archive tabs (planned automation)
When an item's Status is set to Done on the Backlog tab, it should be removed from the 5 working tabs (Backlog, API Design Planning, RTM, Sprint Planning, Release) and its data consolidated into the quarterly archive tab that matches the SPRINT IT WAS DONE IN -- not the date it was archived. E.g. an item done in Sprint 8 goes to 'Q2 Backlog Report 2026', since Sprint 8 falls in Q2. This is automation #6, planned for the same Power Automate rollout as the Jira/Trello automations above: trigger = Status changed to Done on Backlog; action = look up that item's Sprint in the Sprint->Quarter mapping table (Lists sheet, columns K-M) to find the right quarter tab, copy the row's data there (with a Date Archived stamp), then delete it from all 5 working tabs. Not yet wired up -- until then, Done items simply stay in place across the working tabs.
The Sprint->Quarter mapping only covers 2026 right now (Sprint 1-16, Q1-Q4). It will need updating on the Lists sheet every year, since sprint numbering and quarter week boundaries reset annually and a new set of 4 quarterly tabs will need creating for the new year.

## Backlog
Requirement ID | Requirement Name | Type | Stream | Stream Owner | Status | Priority | Planned Delivery | Sprint | HLE | Release | Date Added | Create Jira Ticket? | Jira Key | Jira Link | ID Number
NEW-0002 | Whatsapp Subscription (Phase 2) | CR | Backlog | MA | ON HOLD | Medium | Q4 2026 |  |  |  | 2026-07-23
NEW-0005 | Handling multicabin booking | CR | Growth | B2CW | NEW | Medium | Q4 2026 |  | 21 |  | 2026-07-23
NEW-0006 | New UWO Interface (decoupling) | New | Growth | B2CW | NEW | Medium | Q1 2027 |  | 3 |  | 2026-07-23
NEW-0007 | Update Hold option (decoupling) | CR | Growth | B2CW | NEW | Medium | Q1 2027 |  | 3 |  | 2026-07-23
NEW-0011 | INT 101 - Cabin Selections (Booking Group Management) | CR | Growth | S&S | NEW | Medium | Q4 2026 |  | 8 |  | 2026-07-23 | Created | MDTTPU-8135
NEW-0016 | myMSC Add USA Market Configuration - Chain 1/ Chain 2 | Config | US | B2CW | NEW | Medium | Q3 2026 |  | 8 |  | 2026-07-23 | Created | MDTTPU-13662
NEW-0017 | ARG Payment provider Pagtur | New | MVP Rollout | B2CW | NEW | Medium | Q1 2027 |  | 40 |  | 2026-07-23
NEW-0018 | BR Payment providerDireçao | New | MVP Rollout | B2CW | NEW | Medium | Q1 2027 |  | 40 |  | 2026-07-23
NEW-0020 | MyMSC Spa | New | MyMSC | B2CW | NEW | Medium |  |  | 20 |  | 2026-07-23
NEW-0022 | Super Agency Access | New | MyMSC | B2CW | NEW | Medium |  |  | 8 |  | 2026-07-23
NEW-0033 | Pending Configurations for DACH, MED, LATAM | Config | MyMSC | B2CW | NEW | Medium |  |  | 3 |  | 2026-07-23 | Created | DTTP25-21230
NEW-0068 | [EAINT] [CR][INT026][INT133][INT130] Split calls to CMS for excursion/OBS data into chunks | CR | MyMSC | B2CW | NEW | Medium |  |  | 8 |  | 2026-07-23
NEW-0265 | TLI 99.1 | TBC | US | MA | NA | Medium |  |  |  |  | 2026-07-29
NEW-0266 | Campaigns for loyalty program management | TBC | US | MA | NA | Medium |  |  |  |  | 2026-07-29
NEW-0270 | Booking Group Management Cabin Selections | CR | US | B2CW | NEW | Medium |  |  | 5 |  | 2026-07-29
NEW-0274 | INT024.2 - Addition of “Disembarkation Date” and “Pay By” fields | CR | Growth | S&S | NEW | Medium |  |  | 3 |  | 2026-07-29
NEW-0284 | DACH, MED, LATAM Configurations | CR | MyMSC | B2CW | NEW | Medium |  |  |  |  | 2026-07-29
NEW-0288 | Remove of login endpoints from MyMSC EAPI | Tech Task | MyMSC | ALL | NEW | Medium |  |  | 8 |  | 2026-07-29
NEW-0290 | Bug fix for cabin logic in INT135.1/135.2 | Bug | MyMSC | B2CW | NEW | Medium |  |  |  |  | 2026-07-29
NEW-0299 | Spa | CR | MyMSC | B2CW | NEW | Medium |  |  | 33 |  | 2026-07-29
NEW-0315 | MyMSC CR to handle BKG_001 when booking retrieved | CR | MyMSC | B2CW | NEW | Medium |  |  | 8 |  | 2026-07-29
NEW-0322 | MyMSC/MA CR for enabling DEM links to light login | CR | MyMSC | B2CW | NEW | Medium |  |  | 13 |  | 2026-07-29
NEW-0324 | MSC- MyMSC PRE_CRM_002 error scenario change CR to additem | CR | MyMSC | B2CW | NEW | Medium |  |  |  |  | 2026-07-29
NEW-0343 | CDP / DTS Post Booking - CR - Passenger name filter | CR | Backlog | MA | ON HOLD | Medium |  |  |  |  | 2026-07-29
NEW-0344 | CDP / DTS Post Booking - CR - INT024.1 Improve data quality handling and optimise customer search | CR | Backlog | MA | NEW | Medium |  |  |  |  | 2026-07-29
NEW-0345 | CDP / DTS Post Booking - CR - INT024.1 Long term Improved data quality handling | CR | Backlog | MA | NEW | Medium |  |  |  |  | 2026-07-29
NEW-0346 | CR - Improved data quality handling optimise customer search page size across other integrations | CR | Backlog | MA | NEW | Medium |  |  |  |  | 2026-07-29
NEW-0356 | MED Insurance - Do not sell any insurance if CoR differ across pax | CR | Growth | B2CW | ON HOLD | Medium |  |  | 8 |  | 2026-07-29
NEW-0358 | CMS Configuration for Airports in B2CW Booking Funnel | CR | Growth | B2CW | ON HOLD | Medium |  |  |  |  | 2026-07-29
NEW-0360 | Paypal Reconciliation for prepaid | CR | Growth | B2CW | NEW | Medium | Q4 2026 |  | 5 |  | 2026-07-29
NEW-0361 | US - adding of fields to Hold option orchestration in call to AJO -cabincode, embarkation date, cruise area | CR | Growth | MA | NEW | Medium | Q4 2026 |  |  |  | 2026-07-29
NEW-0362 | US - Known and Unknown management analysis for US (CDP/AJO) | CR | Growth | MA | NEW | Medium | Q4 2026 |  |  |  | 2026-07-29
NEW-0363 | US - Outbound Leads - Light Login for Leads Moving Option Expiring | CR | Growth | B2CW | NEW | Medium | Q4 2026 |  |  |  | 2026-07-29
NEW-0364 | B2CW Booking Funnel - TRF and Pricing Structure Assessment – ESP Market | CR | Growth | B2CW | NEW | Medium | Q4 2026 |  |  |  | 2026-07-29
NEW-0366 | B2CW Accessibility & Medical Webform Business Rules for booking | CR | Growth | B2CW | NEW | Medium | Q4 2026 |  |  |  | 2026-07-29
NEW-0367 | MyMSC US ¦ Extend JWT expiry | CR | Growth | B2CW | NEW | Medium | Q4 2026 |  | 5 |  | 2026-07-29
NEW-0370 | Handling DSC_076 scenario in booking funnel | CR | Growth | B2CW |  | Medium |  |  |  |  | 2026-07-29
NEW-0371 | B2CW Prospect Onsite Quotation | TBC | Growth | B2CW | NEW | Medium |  |  | 5 |  | 2026-07-29
NEW-0373 | Booking Funnel - AI Optimisation | Tech Task | Backlog / Tech Enh | ALL | NEW | Medium |  |  |  |  | 2026-07-29
NEW-0375 | Booking Funnel - OTEL | Tech Task | Backlog / Tech Enh | ALL | IN PROGRESS | Medium |  |  |  |  | 2026-07-29
NEW-0376 | Improve error handling in booking creation | Tech Task | Backlog / Tech Enh | ALL | NEW | Medium |  |  |  |  | 2026-07-29
NEW-0377 | DTTP25-27161 Change payment and newsletter redirection URL logic | Tech Task | Backlog / Tech Enh | ALL | NEW | Medium |  |  |  |  | 2026-07-29
NEW-0384 | New Security Remediation - DTTP Stack to CRM ASIS_EA | CR | PI10 | CRMASIS | NA | Medium |  |  |  |  | 2026-07-29
NEW-0395 | PDF: age restrictions management | CR | MyMSC | B2CW | NEW | Medium | Aug 2026 |  | 5 |  | 2026-07-29
NEW-0397 | MSC Voyagers Club subscription block for pending Status Match request for the same user | CR | MyMSC | B2CW | NEW | Medium | Q1 2027 |  | 8 |  | 2026-07-29
NEW-0398 | MSC Voyagers Club children association | CR | MyMSC | B2CW | NEW | Medium | Q1 2027 |  | 13 |  | 2026-07-29
NEW-0399 | Managing the possibility of multiple categories for the same EXC item | CR | MyMSC | B2CW | NEW | Medium | Q1 2027 |  | 8 |  | 2026-07-29
NEW-0400 | Card Points History Reliability Enhancement - B2C | CR | MyMSC | B2CW | NEW | Medium | Q1 2027 |  | 8 |  | 2026-07-29
NEW-0401 | Excursions' category not visible, neither in the catalogue nor in the modal | CR | MyMSC | B2CW | NEW | Medium | Q1 2027 |  | 8 |  | 2026-07-29
NEW-0402 | Cross Device > Plan my cruise: Cart > Impossible to apply a coupon on a NON-Discounted item | CR | MyMSC | B2CW | NEW | Medium | Q1 2027 |  | 8 |  | 2026-07-29
NEW-0403 | Wider management of label | TBC | MyMSC | B2CW | NEW | Medium | Q1 2027 |  |  |  | 2026-07-29
NEW-0404 | Cross Device > Plan My Cruise > OBS/ACT 'Add passenger' CTA shown even if only non-eligible pax | TBC | MyMSC | B2CW | NEW | Medium | Q1 2027 |  |  |  | 2026-07-29
NEW-0405 | Whatsapp Subscription (Phase 3) | CR | Backlog | MA | NEW | Medium | Q4 2026 |  | 16 |  | 2026-07-30
NEW-0407 | Puerto Rico on US site Status Match (INT010.3) | CR | US |  | NEW | High | Q3 2026 |  | 5 |  | 2026-08-03 | Created | MDTTPU-15251
NEW-0413 | [EINT][INT187][INT139][INT145] - Remove phone number mapping from Datatrans transaction creation | Tech Story | PI10 | M4M | NEW | Medium |  |  |  |  | 2026-08-03 | Created | DTTP25-41728
NEW-0414 | [EINT][INT139][INT140][INT187][INT188] - Fix PromoCodeData coupon/discount code field mapping | Tech Story | PI10 | M4M | NEW | Medium |  |  |  |  | 2026-08-03 | Created | DTTP25-41730
NEW-0415 | [EINT][INT139][INT187][INT140][INT188] - Improve error handling: BKGREQ_098, BKGREQ_050, PPI_DRIPR_11 | Tech Story | PI10 | M4M | NEW | Medium |  |  |  |  | 2026-08-03 | Created | DTTP25-41725
NEW-0032 | Cruise ID / Birthdate missing from A013 and A007 | CR | MyMSC | B2CW | DONE | Medium |  |  | 8 |  | 2026-07-23 | Created | DTTP25-40256
NEW-0047 | Load Test + Performance Enhancements | Tech Task | US | ALL | IN PROGRESS | Medium |  |  | 40 |  | 2026-07-23 | Created | MDTTPU-13969
NEW-0048 | API Prod Configurations | Config | US | B2CW | IN PROGRESS | Medium |  |  | 8 |  | 2026-07-23 | Created | MDTTPU-1292
NEW-0049 | Redo configs of US in Chain 1 branches for non-prod/ prod | Config | US | ALL | IN PROGRESS | Medium |  |  | 8 |  | 2026-07-23 | Created | MDTTPU-13739
NEW-0050 | Redo market routing logic to cover calls to CDP for Chain 1 | Config | US | ALL | IN PROGRESS | Medium |  |  | 13 |  | 2026-07-23 | Created | MDTTPU-13740
NEW-0051 | US Migration to CHAIN1 | Tech Task | US | ALL | IN PROGRESS | High |  |  | 5 |  | 2026-07-23 | Created | MDTTPU-13970
NEW-0053 | US Configuration CHAIN1/2 | Config | MyMSC | B2CW | NEW | Medium |  |  | 8 |  | 2026-07-23 | Created | MDTTPU-13662
NEW-0055 | Release Preparation (Release 15, M4M, US) | Tech Task | Cross | ALL | IN PROGRESS | High |  |  | 21 |  | 2026-07-23 | Created | MDTTPU-13971
NEW-0359 | Paypal Reconciliation for booking payments | CR | Growth | B2CW | DONE | High |  |  | 5 |  | 2026-07-29 | Created | DTTP25-19655
NEW-0392 | INT183 - Add price per night | CR | PI10 | M4M | DONE | High |  |  | 3 |  | 2026-07-29 | Created | EA-1772
NEW-0406 | myMSC Add USA Market Configuration - Production | Config | MyMSC | B2CW | NEW | Medium | Q3 2026 |  | 8 |  | 2026-07-30 | Created | MDTTPU-14018
NEW-0416 | Relax MyArea access rules in LL | CR | MyMSC | B2CW | DONE | Medium |  |  | 5 |  | 2026-08-04 | Created | DTTP25-41462
NEW-0012 | INT 103 - agency email,. Representative code in INT 101/ 103 (webform US) | CR | US | S&S | DONE | Medium |  |  | 5 |  | 2026-07-23 | Created | MDTTPU-6137
NEW-0015 | Tokenisation - CR - INT 007/ INT 146 | CR | US | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-23 | Created | MDTTPU-10926
NEW-0043 | CR INT 113 - FormofPayment (PL) | CR | MyMSC | B2CW | DONE | Medium |  |  | 2 |  | 2026-07-23 | Created | DTTP25-38934
NEW-0044 | CR INT 113/ INT 142 - Group type field | CR | MyMSC | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-23 | Created | DTTP25-38931
NEW-0263 | B2CW Payment Review - Data Lodging - INT140 & INT146 - prepaid/cruise booking myAREA | CR | US | B2CW | DONE | Medium |  |  | 10 |  | 2026-07-29 | Created | MDTTPU-4728
NEW-0264 | Web form for US | CR | US | MA | DONE | Medium |  |  | 6 |  | 2026-07-29 | Created | MDTTPU-6137
NEW-0272 | B2CW Payment Review Tokenisation - CR to update AJO/CDP A013/A070 | CR | US | MA | IN PROGRESS | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-10926
NEW-0292 | INT139 / INT140 - CR - Klarna Prepaid + PDC Customer Contacts | CR | MyMSC | B2CW | DONE | Medium |  |  | 16 |  | 2026-07-29 | Created | DTTP25-35604
NEW-0293 | INT145 - CR - Klarna - MyMSC Checkout Payment Support | CR | MyMSC | B2CW | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | DTTP25-35603
NEW-0313 | Idempotency on booking payments | CR | MyMSC | B2CW | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | DTTP25-36938
NEW-0341 | DTS Post Booking Migration - Market US + CAN | CR | Backlog | MA | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | DTTP25-38409
NEW-0342 | CDP / DTS Post Booking - CR - Pax details Change | CR | Backlog | MA | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | DTTP25-36972
NEW-0380 | MSC4Me Precruise - Prepaids flow indipendence | New | PI9 | M4M | DONE | Medium |  |  |  |  | 2026-07-29 | Created | EA-1117
NEW-0042 | Idempotency Key for Prepaids + Refund | CR | MyMSC | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-23 |  | DTTP25-36939
NEW-0417 | Configure APIs for India | Config | MVP Rollout | B2CW | DONE | Medium |  |  | 8 |  | 2026-08-04 | Created | DTTP25-40332
NEW-0418 | INT146 - CR - Klarna - MyMSC Post-Booking Payment Support | CR | MyMSC | B2CW | DONE | Medium |  |  | 13 |  | 2026-08-04 | Created | DTTP25-38635
NEW-0063 | INT 005.2 - Support One-Way Air Packages in Flight Availability | CR | Growth | B2CW | DONE | Critical |  |  | 5 |  | 2026-07-23 | Created | DTTP25-37438
NEW-0112 | Lead pax details in booking event | CR | US | S&S | DONE | Medium |  |  |  |  | 2026-07-29 | Created | DTTP25-36972
NEW-0113 | INT 710 Timezone Lookup | CR | US | S&S | DONE | Medium |  |  |  |  | 2026-07-29 | Created | MDTTPU-6141
NEW-0120 | INT 101 - Add group id in webforms | CR | US | S&S | DONE | Medium |  |  |  |  | 2026-07-29 | Created | MDTTPU-8133
NEW-0121 | INT 024.1/ INT 025/ INT100 - Add group type field | CR | US | S&S | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | MDTTPU-6140
NEW-0122 | INT 037 - B2B Representative Event | New | US | S&S | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-2675
NEW-0151 | INT 139 / 140 - additional applicability logic | CR | MyMSC | B2CW | DONE | Medium |  |  |  |  | 2026-07-29 | Created | DTTP25-35437
NEW-0219 | INT710 - Outbound leads - Abandoned Cart - Genesys Contact ID Mapping and Multiple Case Handling | CR | US | S&S | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-5929
NEW-0228 | INT114.1 / INT114.2 / INT113 Limit access to bookings from the same office as the website agency | CR | MyMSC | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | DTTP25-38013
NEW-0233 | [CR] Booking Funnel Market Segregation - Include market-level data in logging | Tech Task | Tech | ALL | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | DTTP25-34120
NEW-0234 | LOAD TEST in Perf Env - Part 2 | Tech Task | Tech | ALL | DONE | Medium |  |  | 5 |  | 2026-07-29
NEW-0242 | PVC - INT024.2 CR | CR | US | S&S | DONE | Medium |  |  | 2 |  | 2026-07-29 | Created | MDTTPU-4777
NEW-0247 | Attentive - INT172 | New | US | MA | DONE | Medium |  |  | 21 |  | 2026-07-29
NEW-0248 | Attentive - INT174 | New | US | MA | DONE | Medium |  |  | 8 |  | 2026-07-29
NEW-0267 | Outbound leads - Abandoned Cart - Replacement of Salescycle | TBC | US | MA | ON HOLD | Medium |  |  |  |  | 2026-07-29
NEW-0269 | Pre-booking customisation - Free Balcony Upgrades | CR | US | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | MDTTPU-9536
NEW-0271 | INT 002 CR - Kids Sail Free | CR | US | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-7976
NEW-0304 | INT139 / INT140 - Applicability of items during all inclusive logic - CR passenger type logic | CR | MyMSC | B2CW | DONE | Medium |  |  | 2 |  | 2026-07-29 | Created | DTTP25-37982
NEW-0310 | Super Agency Access - Short term workaround CR | CR | MyMSC | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | DTTP25-38013
NEW-0312 | INT114 Modify rule on departure date | CR | MyMSC | B2CW | DONE | Medium |  |  | 2 |  | 2026-07-29 | Created | DTTP25-35435
NEW-0388 | DTTP - Sign Up Event Tracking in AEP/AJO/CDP/SALESFORCE_EAImpact | CR | PI10 | MA | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | EA-1307
NEW-0390 | CRM - Consent Management - Profiling info in the Customer Event table CDP/AJ0_EAImpact |  | PI10 |  | NEW | Medium |  |  | 5 |  | 2026-07-29 | Created | EA-1327
NEW-0420 | INT 004.3/004.4/006/007 - Forward airType to DTS in Insurance, Price, Booking, and Hold Option Requests (One-Way Air Packages) | CR | Growth | B2CW | DONE | Critical |  |  | 13 |  | 2026-08-04 | Created | DTTP25-37439
NEW-0421 | INT 002.x - Expose airType in Category Search Responses (One-Way Air Packages) | CR | Growth | B2CW | DONE | Critical |  |  | 5 |  | 2026-08-04 | Created | DTTP25-31684
NEW-0422 | [Rollout] Configure APIs for India - CHAIN1&2 Config | Config | MVP Rollout | B2CW | DONE | Medium |  |  | 8 |  | 2026-08-04 | Created | DTTP25-39645
NEW-0100 | Call me back / Already sent | CR | US | S&S | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | MDTTPU-4412
NEW-0103 | Outbound leads - Abandoned Cart - New Interface INT007.2 | CR | US | B2CW | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | MDTTPU-5928
NEW-0104 | Outbound leads - Abandoned Cart - Change to INT710 | CR | US | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29
NEW-0105 | Uknown Web Option | CR | US | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29
NEW-0111 | INT 158 - Assign Opportunity ID to existing booking | New | US | S&S | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-1816
NEW-0127 | Flight classes | CR | Growth | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | DTTP25-35414
NEW-0131 | Datatrans webhook INT165 inc. routing to AZF005 | CR | Growth | B2CW | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | DTTP25-36856
NEW-0143 | INT 130 - Dining Slots CR | CR | MyMSC | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | DTTP25-35956
NEW-0146 | INT 139/ INT 140 Applicability ALL INC | CR | MyMSC | B2CW | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | DTTP25-35437
NEW-0148 | Already Purchased - item no longer sold - INT 142 | CR | MyMSC | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | DTTP25-37062
NEW-0150 | INT 139/140 -all inc item missing from OBS List | CR | MyMSC | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29
NEW-0240 | Setup of DTS credit card codes for US | CR | US | S&S | DONE | Medium |  |  | 2 |  | 2026-07-29 | Created | MDTTPU-6139
NEW-0243 | PVC - INT158 (New Interface) | New | US | S&S | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-1336
NEW-0246 | Attentive - INT175 | New | US | MA | DONE | Medium |  |  | 5 |  | 2026-07-29
NEW-0253 | Outbound leads - Already Sent | CR | US | S&S | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | MDTTPU-2573
NEW-0257 | DTS-Salesforce Optimisations - INT 037 | New | US | S&S | DONE | Medium |  |  | 5 |  | 2026-07-29
NEW-0268 | Not To Sail | CR | US | S&S | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-6142
NEW-0291 | INT159 - Lab item for myMSC | New | MyMSC | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 |  | DTTP25-35279
NEW-0294 | INT142 fix for flights | CR | MyMSC | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29
NEW-0303 | INT139 / INT140 - Applicability of items during all inclusive logic - CR related items | CR | MyMSC | B2CW | DONE | Medium |  |  | 8 |  | 2026-07-29
NEW-0305 | INT130 / INT139 / INT140 - Applicability of Items - Switch to new cache jsononboardservice | CR | MyMSC | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | DTTP25-36730
NEW-0307 | INT140 handling of coupons - error handling | CR | MyMSC | B2CW | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | DTTP25-34505
NEW-0319 | INT 163 - Add missing PrepaidShop field | CR | MyMSC | B2CW | DONE | Medium |  |  | 2 |  | 2026-07-29 | Created | DTTP25-36916
NEW-0352 | INT165 - Datatrans Webhook v1.0 | New | Growth | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | DTTP25-34473
NEW-0357 | PDC - Customer Contacts - B2C Funnel Alignment | CR | Growth | B2CW | DONE | Medium |  |  | 21 |  | 2026-07-29 | Created | DTTP25-35415
NEW-0387 | DTTP - Lead Management - Web forms - Market-Based Date Format Localization | CR | PI10 | MA | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | EA-1280
NEW-0108 | Web user cancellation - INT 121 | CR | US | S&S | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-2673
NEW-0109 | Web user cancellation - INT118 | New | US | S&S | DONE | Medium |  |  | 13 |  | 2026-07-29 | Created | MDTTPU-2674
NEW-0135 | INT 135.1 - Shop Request CR | CR | MyMSC | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | DTTP25-31539
NEW-0136 | INT 142 - Add thematic Booking id | CR | MyMSC | B2CW | DONE | Medium |  |  | 2 |  | 2026-07-29 | Created | DTTP25-34294
NEW-0137 | [INT 136.1 - Thematic Availability (Speciality Restaurant) | New | MyMSC | B2CW | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | DTTP25-34293
NEW-0138 | INT 139/ INT 140 CR - Pricetobook / bookprepaid itesm | CR | MyMSC | B2CW | DONE | Medium |  |  | 13 |  | 2026-07-29 | Created | DTTP25-34295
NEW-0139 | INT 163 - Thematic Revise | New | MyMSC | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | DTTP25-34475
NEW-0142 | INT 139/ INT 140 CR - Item unavailablility | CR | MyMSC | B2CW | DONE | Medium |  |  | 13 |  | 2026-07-29 | Created | DTTP25-35278
NEW-0153 | Outbound leads - Unknown web option | CR | US | MA | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | MDTTPU-5927
NEW-0187 | Update configurations for Turkey | Config | MVP Rollout | B2CW | DONE | Medium |  |  | 2 |  | 2026-07-29 | Created | DTTP25-35439
NEW-0188 | DTS Post Booking - Load Test Activities + New Volumes Support | Tech Task | Backlog | ALL | DONE | High |  |  | 18 |  | 2026-07-29 | Created | DTTP25-35644
NEW-0190 | Outbound leads - Hold Option - INT004.4 | CR | US | MA | DONE | Medium |  |  | 21 |  | 2026-07-29 | Created | MDTTPU-5925
NEW-0192 | [MyArea] Re-captcha keys - Lower environment TEST | Tech Task | MyMSC | B2CW | DONE | Medium |  |  | 2 |  | 2026-07-29 | Created | DTTP25-35257
NEW-0256 | Outbound leads - Hold Option - INT006 | CR | US | B2CW | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | MDTTPU-5926
NEW-0283 | [EINT] Campaign codes for UK/IE myMSC - New HQ Sandbox | CR | MyMSC | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | DTTP25-34495
NEW-0287 | INT145/146 Revised payment options | CR | MyMSC | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | DTTP25-14439
NEW-0289 | [EINT] [CR] INT 139/ 140 - Item unavailability | CR | MyMSC | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | DTTP25-35278
NEW-0295 | Specialty Restaurants - INT135, INT139, INT140, INT142 | CR | MyMSC | B2CW | DONE | Medium |  |  | 18 |  | 2026-07-29 | Created | DTTP25-31539
NEW-0296 | Specialty Restaurants - INT136, INT163 | New | MyMSC | B2CW | DONE | Medium |  |  | 13 |  | 2026-07-29 | Created | DTTP25-34475
NEW-0298 | Consent Management | CR | MyMSC | B2CW | DONE | Medium |  |  | 13 |  | 2026-07-29 | Created | DTTP25-29365
NEW-0300 | INT137 - Refund: improve long processing time | CR | MyMSC | B2CW | DONE | Medium |  |  | 21 |  | 2026-07-29 | Created | DTTP25-14697
NEW-0386 | Support for the enabling of IP whitelist for Mulesoft Marketo | CR | PI10 | MA | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | EA-1125
NEW-0123 | Data Lodging - INT 007 | CR | US | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-2694
NEW-0249 | Pre Booking Customisation - INT017v1 - Ship Postion | CR | US | B2CW | DONE | Medium |  |  | 2 |  | 2026-07-29 | Created | MDTTPU-1817
NEW-0250 | Pre Booking Customisation - INT 007/006 - Error management – Fully booked cabin | CR | US | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-1818
NEW-0251 | Pre Booking Customisation - Refresh availability – Change to INT 002 | CR | US | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-3291
NEW-0252 | Pre Booking Customisation - OBC Pills | CR | US | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-2801
NEW-0260 | B2CW Payment Review - Tokenisation (Booking Funnel) | CR | US | B2CW | DONE | Medium |  |  | 13 |  | 2026-07-29 | Created | MDTTPU-2693
NEW-0261 | B2CW Payment Review - Tokenisation (myMSC) | CR | US | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-4426
NEW-0262 | B2CW Payment Review - Data lodging - cruise booking - Booking funnel | CR | US | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-2597
NEW-0306 | INT139 handling of coupons | CR | MyMSC | B2CW | DONE | Medium |  |  | 13 |  | 2026-07-29 | Created | DTTP25-34471
NEW-0308 | Voyager Club - INT152 - Add Total Points per cruise | CR | MyMSC | B2CW | DONE | Medium |  |  | 2 |  | 2026-07-29 | Created | DTTP25-32814
NEW-0309 | INT139 Add new field regarding coupon discount | CR | MyMSC | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | DTTP25-33595
NEW-0339 | CDP / DTS Post Booking - CR - Beverage/ Bundle Campaigns | CR | Backlog | MA | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | DTTP25-34477
NEW-0382 | DTTP - MA - Integration between AJO and OBR/Shorex Platform/Catalog [ANALYSIS]_EA | CR | PI9 | MA | DONE | Medium |  |  |  |  | 2026-07-29 | Created | CRM2-5703
NEW-0099 | Verbal DNC | CR | US | S&S | DONE | Medium |  |  |  |  | 2026-07-29 | Created | MDTTPU-1452
NEW-0133 | Error mapping INT 140 - Promo no longer available | CR | MyMSC | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | DTTP25-31218
NEW-0239 | [EAINT] [CR] Missing market code PAPI | Config | US | MA | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | MDTTPU-4055
NEW-0282 | Light Login Flow for DEM Email | CR | MyMSC | B2CW | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | DTTP25-14580
NEW-0286 | Error Management - Promotion no longer available – Change to INT 140 | CR | MyMSC | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | DTTP25-31218
NEW-0337 | INT024.1 - Changes to accommodate DTS Post Booking | CR | Backlog | MA | DONE | Medium |  |  | 42 |  | 2026-07-29 | Created | DTTP25-15335
NEW-0338 | CDP / DTS Post Booking MuleSoft Scalability, Performance, Resilience Assessment | Tech Task | Backlog | ALL | DONE | Medium |  |  | 4 |  | 2026-07-29 | Created | DTTP25-36961
NEW-0350 | INT 004.4 - Update to support Klarna payment method | CR | Growth | B2CW | DONE | Medium |  |  | 13 |  | 2026-07-29 | Created | DTTP25-31069
NEW-0351 | Klarna - Itinerary cache - shared access | CR | Growth | B2CW | DONE | Medium |  |  | 5 |  | 2026-07-29 | Created | DTTP25-32844
NEW-0419 | INT004.4 - Enable Klarna Webhook URL (dtt-payment-sapi) | New | Growth | B2CW | DONE | Medium |  |  |  |  | 2026-08-04 | Created | DTTP25-38109
NEW-0423 | INT 007 - Update to support Klarna payment method | CR | Growth | B2CW | DONE | Medium |  |  | 3 |  | 2026-08-04 | Created | DTTP25-31070
NEW-0424 | INT100 - BookingProfileOrchestration (New Interface, DTS Post Booking) | New | Backlog | MA | DONE | Medium |  |  |  |  | 2026-08-05 | Created | DTTP25-15383
NEW-0425 | INT025 - BookingEventOrchestration (New Interface, DTS Post Booking) | New | Backlog | MA | DONE | Medium |  |  |  |  | 2026-08-05 | Created | DTTP25-15384
NEW-0093 | [CR] [EAINT] INT069: Marketing SAPI / CRM EAPI updates to support routing to CDP based on market code | CR | US | MA | DONE | Medium |  |  | 2 |  | 2026-07-29 | Created | MDTTPU-1248
NEW-0094 | [CR] [EAINT] INT077: Dual CDP (US and HQ) Loading with Retry Logic | CR | US | MA | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | MDTTPU-1255
NEW-0236 | GBP Enablement | CR | PP | B2CW | DONE | Medium |  |  | 2 |  | 2026-07-29 | Created | FFPP-348
NEW-0241 | PVC - INT069 CR | CR | US | S&S | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | MDTTPU-1450
NEW-0245 | Do not Call INT044, INT014, INT500 | CR | US | S&S | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | MDTTPU-1452
NEW-0285 | Update Excursions node in INT140 request | CR | MyMSC | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | DTTP25-29370
NEW-0330 | Emergent Markets (PL-TR-MT) APIs Configuration - CHAIN1/2, Prod | Config | MVP Rollout | B2CW | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | DE-39
NEW-0331 | Accessibility Form - "Transfer between checking and boarding gate" new field CR | CR | MVP Rollout | B2CW | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | DTTP25-31264
NEW-0374 | [Load Test] Prepare new environement for load testing activities | Tech Task | Backlog / Tech Enh | ALL | DONE | Medium |  |  | 21 |  | 2026-07-29 | Created | DTTP25-32150
NEW-0383 | DTTP - MA - B2B2C App Check-in On Demand (MSC Book)_EA | CR | PI9 | MA | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | EA-1124
NEW-0001 | Whatsapp Subscription (Phase 1) | New | Backlog | MA | NEW | Medium | Q3 2026 |  | 13 |  | 2026-07-23 | Created | DTTP25-36678
NEW-0003 | Friends and Family INT 157 | New | Backlog | S&S | NEW | Medium |  |  | 13 |  | 2026-07-23 | Created | DTTP25-36959
NEW-0029 | MYMSC All inc CR remove logic from AEM | CR | MyMSC | B2CW | NEW | Medium | 2026-08-01 |  | 29 |  | 2026-07-23 | Created | DTTP25-38250
NEW-0030 | Handling of additional errors INT 139/ INT 140 | CR | MyMSC | B2CW | NEW | Medium |  |  | 8 |  | 2026-07-23 | Created | DTTP25-40357
NEW-0080 | Hypercare | Tech Task | US | ALL | NEW | High |  |  |  |  | 2026-07-23
NEW-0084 | PI11-07 [B2C] Hold Option (Placeholder - MuleSoft should not be involved) | TBC | PI11 | B2CW | NEW | Medium |  |  |  |  | 2026-07-23
NEW-0085 | PI11-08 [CDP] [INTP-21] Lead Management - Option event creation in CDP | CR | PI11 | MA | NEW | Medium |  |  | 5 |  | 2026-07-23 | Created | DTTP25-41937
NEW-0086 | PI11-11 [CRM] [EA-1008] DTTP - Lead Management - FCC new outbound sources | CR | PI11 | MA | NEW | Medium |  |  | 8 |  | 2026-07-23 | Created | DTTP25-41939
NEW-0087 | PI11-12 [CDP/CRM] CRM2-11097 / [INTP-20] Lead Management - IRL Outbound Sources Activation & Form Creation | CR | PI11 | MA | NEW | Medium |  |  | 5 |  | 2026-07-23 | Created | DTTP25-41940
NEW-0316 | INT139 / INT140 - speciality restaurants CR to handle dining inventory errors | CR | MyMSC | B2CW | NEW | Medium |  |  | 8 |  | 2026-07-29 | Created | DTTP25-40356
NEW-0064 | ZAF Rollout - Market Configurations in CHAIN1 & CHAIN2 | Config | MVP Rollout | B2CW | NEW | Medium |  |  | 8 |  | 2026-07-23 | Created | DTTP25-41351
NEW-0065 | ZAFRollout - Market Configurations in Production | Config | MVP Rollout | B2CW | NEW | Medium |  |  | 8 |  | 2026-07-23 | Created | DTTP25-41351
NEW-0066 | PI11-03 [B2C] Flight Enhancement - DTTP25-38915 | CR | PI11 | B2CW | NEW | Medium |  |  | 5 |  | 2026-07-23 | Created | DTTP25-41930
NEW-0067 | PI11-14 [CRM] [EA-1722] CRM Dependency - Lead Management - Price Description info in CDP | CR | PI11 | MA | NEW | Medium |  |  | 8 |  | 2026-07-23 | Created | DTTP25-41931
NEW-0072 | PI11-04 [B2C] Post Cruise Complaint Form Part 2 (Multiple Attachment) - DTTP25-38913 | CR | PI11 | B2CW | NEW | Medium |  |  | 21 |  | 2026-07-23 | Created | DTTP25-41932
NEW-0073 | PI11-05 [B2C] Accessibility Form - DTTP25-38914 | CR | PI11 | B2CW | NEW | Medium |  |  |  |  | 2026-07-23 | Created | DTTP25-41933
NEW-0074 | PI11-06 [B2C] Cabin Position - DTTP25-40042 | CR | PI11 | B2CW | NEW | Medium |  |  | 5 |  | 2026-07-23 | Created | DTTP25-41934
NEW-0075 | PI11-13 [CRM] [INTP-25] CRM Dependency - Marketing Automation - Calculated fields Booking B2B/B2C | CR | PI11 | MA | NEW | Medium |  |  | 13 |  | 2026-07-23 | Created | DTTP25-41935
NEW-0076 | PI11-15 [CRM] [EA-1662] CRM Dependency - Lead Management - Hold option additional event fields in CDP | CR | PI11 | MA | NEW | Medium |  |  | 13 |  | 2026-07-23 | Created | DTTP25-41936
NEW-0077 | Nordics SWE, DEN, NOR, FIN Rollout - Market Configurations in CHAIN1 & CHAIN2 | Config | MVP Rollout | B2CW | NEW | Medium |  |  | 8 |  | 2026-07-23 | Created | DTTP25-37831
NEW-0078 | Nordics SWE, DEN, NOR, FIN Rollout - Market Configurations in Production | Config | MVP Rollout | B2CW | NEW | Medium |  |  | 8 |  | 2026-07-23 | Created | DTTP25-37831
NEW-0409 | US Growth - B2CW Payment billing data/ US Release ACS Check - Part 2 (Wiring the new fields to Datatrans in INT007, INT140, INT146) | CR | Growth | B2CW | ON HOLD | High | Q3 2026 |  | 13 |  | 2026-08-03 | Created | MDTTPU-15253
NEW-0410 | US Growth - M4M Payment billing data/ US Release ACS Check (Adding the fields in M4M transaction init) | CR | Growth | B2CW | ON HOLD | High | Q3 2026 |  | 8 |  | 2026-08-03 | Created | MDTTPU-15254
NEW-0057 | API Prod Configurations - Attentive / Webforms | Config | US | B2CW | NEW | High |  |  | 8 |  | 2026-07-23 | Created | MDTTPU-14019
NEW-0058 | CR - Attentive Error Scenarios INT 175 | CR | US | MA | NEW | Medium |  |  | 5 |  | 2026-07-23 | Created | MDTTPU-13413
NEW-0060 | US Configuration myMSC - Production | Config | US | B2CW | NEW | High |  |  | 8 |  | 2026-07-23 | Created | MDTTPU-14018
NEW-0061 | Load Test + Performance Enhancements - Part 2 | Tech Task | US | ALL | NEW | High |  |  | 21 |  | 2026-07-23 | Created | MDTTPU-15260
NEW-0071 | E2E Ticket Support - FAT and Canary Tests | Tech Task | US | ALL | NEW | High |  |  | 13 |  | 2026-07-23 | Created | DTTP25-41779
NEW-0275 | [EINT] [Tech Task] INT172 INT174 - Attentive Error Scenarios | Tech Task | US | MA | IN PROGRESS | Medium |  |  | 5 |  | 2026-07-29 | Created | MDTTPU-13796
NEW-0368 | MyMSC US ¦ [INT112][INT137][INT140][INT146][INT153][INT154][INT188] Add per-country/language MyMSC campaign config check to skip optional marketing automation calls | CR | Growth | MA | NEW | High |  |  | 8 |  | 2026-07-29 | Created | MDTTPU-14929
NEW-0389 | [DTTP] Implementation of Online Post-Cruise Complaint Form – Salesforce Integration_EA | CR | PI10 | B2CW | NEW | Medium |  |  | 8 |  | 2026-07-29 | Created | DTTP25-40322
NEW-0408 | US Growth - B2CW Payment billing data/ US Release ACS Check - Part 1 (Adding the new fields to INT007, INT140, INT146) | CR | Growth | B2CW | ON HOLD | High | Q3 2026 |  | 5 |  | 2026-08-03 | Created | MDTTPU-15252
NEW-0411 | Load Test Perf - Support & Analysis | Tech Task | US | ALL | NEW | High |  |  | 21 |  | 2026-08-03 | Created | MDTTPU-15252
NEW-0412 | US 0.1 Release Preparation - Aug 24 | Tech Task | Cross | ALL | NEW | High |  |  | 13 |  | 2026-08-03 | Created | MDTTPU-15262
NEW-0090 | API Configurations for US market | Config | US | ALL | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | MDTTPU-1291
NEW-0235 | Phase 1 Payment Auth CR | CR | PP | B2CW | DONE | Medium |  |  | 21 |  | 2026-07-29 | Created | FFPP-337
NEW-0237 | US configurations - Chain 1 / Chain 2 | Config | US | B2CW | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | MDTTPU-1291
NEW-0238 | CDP Sandbox Support for US | Config | US | MA | DONE | Medium |  |  | 3 |  | 2026-07-29 | Created | MDTTPU-1285
NEW-0329 | LATAM Configurations - Chain1 / Chain 2 / Prod | Config | MVP Rollout | B2CW | DONE | Medium |  |  | 7 |  | 2026-07-29 | Created | DTTP25-25776
NEW-0336 | Consent Management | CR | Backlog | B2CW | DONE | Medium |  |  | 23 |  | 2026-07-29 | Created | DTTP25-28557
NEW-0372 | Booking Funnel - Market Segregation | Tech Task | Backlog / Tech Enh | ALL | DONE | Medium |  |  | 16 |  | 2026-07-29 | Created | DTTP25-27361
NEW-0379 | Attentive Marketo CR | CR | PI9 | MA | DONE | Medium |  |  | 8 |  | 2026-07-29 | Created | EA-1097
NEW-0381 | ALT Text - Enhancement | CR | PI9 | B2CW | DONE | Medium |  |  | 2 |  | 2026-07-29 | Created | EA-1154
NEW-0391 | Rosetta Stone | New | HR | ALL | DONE | Medium | Q1 2026 |  | 8 |  | 2026-07-29 | Created | EA-1130
NEW-0426 | INT182 - Add onboard price and exclusive discount flag | CR | PI10 | M4M | DONE | High |  |  | 3 |  | 2026-08-05 | Created | EA-1774
NEW-0427 | INT181 - Add OBS category type | CR | PI10 | M4M | DONE | High |  |  | 3 |  | 2026-08-05 | Created | EA-1775
NEW-0428 | INT181/INT183 - Add linked item code | CR | PI10 | M4M | DONE | High |  |  | 3 |  | 2026-08-05 | Created | EA-1773

## API Design Planning
Requirement ID | Requirement Name | Stream | Jira Link | Status | Sprint | RAML Required | RAML Delivery Date | Assignee | Priority | Design Status | Handover
NEW-0001
NEW-0002
NEW-0003
NEW-0005
NEW-0006
NEW-0007
NEW-0011
NEW-0012
NEW-0015
NEW-0016
NEW-0017
NEW-0018
NEW-0020
NEW-0022
NEW-0029
NEW-0030
NEW-0032
NEW-0033
NEW-0043
NEW-0044
NEW-0047
NEW-0048
NEW-0049
NEW-0050
NEW-0051
NEW-0053
NEW-0055
NEW-0057
NEW-0058
NEW-0060
NEW-0061
NEW-0063
NEW-0064
NEW-0065
NEW-0066
NEW-0067
NEW-0068
NEW-0071
NEW-0072
NEW-0073
NEW-0074
NEW-0075
NEW-0076
NEW-0077
NEW-0078
NEW-0080
NEW-0084
NEW-0085
NEW-0086
NEW-0087
NEW-0090
NEW-0093
NEW-0094
NEW-0099
NEW-0100 | [5 empty] | No
NEW-0103 | [5 empty] | Yes
NEW-0104 | [5 empty] | No
NEW-0105 | [5 empty] | No
NEW-0108 | [5 empty] | Yes
NEW-0109 | [5 empty] | Yes
NEW-0111 | [5 empty] | Yes
NEW-0112 | [5 empty] | No
NEW-0113 | [5 empty] | No
NEW-0120 | [5 empty] | Yes
NEW-0121 | [5 empty] | No
NEW-0122 | [5 empty] | No
NEW-0123 | [5 empty] | No
NEW-0127
NEW-0131
NEW-0133 | [5 empty] | Yes
NEW-0135 | [5 empty] | Yes
NEW-0136 | [5 empty] | Yes
NEW-0137 | [5 empty] | Yes
NEW-0138 | [5 empty] | Yes
NEW-0139 | [5 empty] | Yes
NEW-0142 | [5 empty] | Yes
NEW-0143 | [5 empty] | Yes
NEW-0146 | [5 empty] | Yes
NEW-0148 | [5 empty] | Yes
NEW-0150 | [5 empty] | No
NEW-0151
NEW-0153
NEW-0187
NEW-0188
NEW-0190
NEW-0192
NEW-0219
NEW-0228
NEW-0233
NEW-0234
NEW-0235
NEW-0236
NEW-0237
NEW-0238
NEW-0239 | [9 empty] | Ready for Development
NEW-0240 | [9 empty] | Ready for Development
NEW-0241
NEW-0242 | [9 empty] | Ready for Development
NEW-0243 | [9 empty] | Ready for Development
NEW-0245
NEW-0246 | [9 empty] | Ready for Development
NEW-0247 | [9 empty] | Ready for Development | Yes
NEW-0248 | [9 empty] | Ready for Development | Yes
NEW-0249 | [9 empty] | Ready for Development
NEW-0250 | [9 empty] | Ready for Development
NEW-0251 | [9 empty] | Ready for Development
NEW-0252 | [9 empty] | Ready for Development
NEW-0253 | [9 empty] | Ready for Development
NEW-0256
NEW-0257 | [9 empty] | Ready for Development
NEW-0260 | [9 empty] | Ready for Development
NEW-0261 | [9 empty] | Ready for Development
NEW-0262 | [9 empty] | Ready for Development
NEW-0263 | [9 empty] | Ready for Development
NEW-0264 | [9 empty] | Ready for Development | Yes
NEW-0265 | [9 empty] | Pending Solution
NEW-0266 | [9 empty] | Pending Solution
NEW-0267 | [9 empty] | Pending Solution
NEW-0268 | [9 empty] | Ready for Development
NEW-0269 | [9 empty] | Ready for Development | Yes
NEW-0270 | [9 empty] | Pending Solution
NEW-0271 | [9 empty] | Ready for Development | Yes
NEW-0272 | [9 empty] | Ready for Development | Yes
NEW-0274 | [9 empty] | Pending Design | Yes
NEW-0275 | [9 empty] | Ready for Development | Yes
NEW-0282
NEW-0283
NEW-0284 | [9 empty] | Ready for Development
NEW-0285
NEW-0286
NEW-0287
NEW-0288 | [9 empty] | Ready for Development | Yes
NEW-0289
NEW-0290 | [9 empty] | Ready for Development | Yes
NEW-0291 | [9 empty] | Ready for Development
NEW-0292 | [9 empty] | Ready for Development | Yes
NEW-0293 | [9 empty] | Ready for Development | Yes
NEW-0294 | [9 empty] | Ready for Development
NEW-0295
NEW-0296
NEW-0298
NEW-0299 | [9 empty] | Pending Solution
NEW-0300
NEW-0303 | [9 empty] | Ready for Development
NEW-0304 | [9 empty] | Ready for Development
NEW-0305 | [9 empty] | Ready for Development
NEW-0306
NEW-0307 | [9 empty] | Ready for Development
NEW-0308
NEW-0309
NEW-0310 | [9 empty] | Ready for Development
NEW-0312 | [9 empty] | Ready for Development
NEW-0313 | [9 empty] | Ready for Development
NEW-0315 | [9 empty] | Pending Solution
NEW-0316 | [9 empty] | Pending Solution
NEW-0319
NEW-0322 | [9 empty] | Pending Design
NEW-0324 | [9 empty] | Pending Solution
NEW-0329 | [9 empty] | No Design Required
NEW-0330 | [9 empty] | No Design Required
NEW-0331
NEW-0336
NEW-0337
NEW-0338
NEW-0339 | [9 empty] | Ready for Development
NEW-0341 | [9 empty] | Ready for Development | Yes
NEW-0342 | [9 empty] | Ready for Development | Yes
NEW-0343
NEW-0344 | [9 empty] | Pending Solution
NEW-0345 | [9 empty] | Pending Solution
NEW-0346 | [9 empty] | Pending Solution
NEW-0350
NEW-0351
NEW-0352 | [9 empty] | Ready for Development
NEW-0356
NEW-0357 | [9 empty] | Ready for Development
NEW-0358
NEW-0359 |  |  |  | DONE | [5 empty] | Ready for Development
NEW-0360 | [9 empty] | Pending Solution
NEW-0361 | [9 empty] | Pending Solution
NEW-0362 | [9 empty] | Pending Solution
NEW-0363
NEW-0364
NEW-0366 | [9 empty] | Pending Solution
NEW-0367 | [9 empty] | Pending Solution
NEW-0368 | [9 empty] | Pending Design
NEW-0370
NEW-0371 | [9 empty] | Pending Solution
NEW-0372
NEW-0373 | [9 empty] | Ready for Development
NEW-0374
NEW-0375
NEW-0376 | [9 empty] | Pending Solution
NEW-0377
NEW-0379
NEW-0380
NEW-0381
NEW-0382
NEW-0383
NEW-0384
NEW-0386
NEW-0387
NEW-0388 | [9 empty] | Pending Solution | Yes
NEW-0389 | [9 empty] | Ready for Development
NEW-0390 | [9 empty] | Pending Solution | Yes
NEW-0391
NEW-0392 | [9 empty] | Ready for Development
NEW-0395
NEW-0397
NEW-0398
NEW-0399
NEW-0400
NEW-0401
NEW-0402
NEW-0403
NEW-0404
NEW-0042 | [9 empty] | Ready for Development
NEW-0405
NEW-0416
NEW-0417
NEW-0418 | [5 empty] | Yes |  |  |  | Ready for Development
NEW-0419
NEW-0420
NEW-0421
NEW-0422
NEW-0423
NEW-0406
NEW-0407
NEW-0408
NEW-0409
NEW-0410
NEW-0411
NEW-0412
NEW-0413
NEW-0414
NEW-0415
NEW-0424
NEW-0425
NEW-0426 | [9 empty] | Ready for Development
NEW-0427 | [9 empty] | Ready for Development
NEW-0428 | [9 empty] | Ready for Development

## RTM
Requirement ID | Requirement Name | Stream | Stream Owner | Jira Link | HLD Completed | LLD Completed | Sprint | Status | Priority | Predecessor Stream | Predecessor Task | Predecessor Jira Link | Successor Stream | Successor Jira Link | Dependency Status | Notes
NEW-0001 |  |  |  |  | Yes | Yes |  |  |  | CHUB | Update to CH042 on profiling consents
NEW-0002
NEW-0003 |  |  |  |  | Yes | Yes |  |  |  | S&S | Updates to S008 |  | F&F | https://smartship.atlassian.net/browse/DTTP25-352
NEW-0005 |  |  |  |  | No | No
NEW-0006 |  |  |  |  | No | No
NEW-0007 |  |  |  |  | No | No
NEW-0011 |  |  |  |  | No | No
NEW-0012 |  |  |  |  | Yes | Yes |  |  |  |  | S&S to add fields in case | https://smartship.atlassian.net/browse/MDTTPU-3723 |  | https://smartship.atlassian.net/browse/MB-6912
NEW-0015 |  |  |  |  | Yes | Yes |  |  |  |  | Tokenisation Flag - A070/ A013 | https://smartship.atlassian.net/browse/MDTTPU-8082
NEW-0016 |  |  |  |  | No | No
NEW-0017 |  |  |  |  | No | No
NEW-0018 |  |  |  |  | No | No
NEW-0020 |  |  |  |  | No | No
NEW-0022 |  |  |  |  | No | No |  |  |  |  | To confirm
NEW-0029 |  |  |  |  | Yes | No |  |  |  | DTS | Updates in GetBookings | https://smartship.atlassian.net/browse/RES2-29207, https://smartship.atlassian.net/browse/RES2-29208, https://smartship.atlassian.net/browse/RES2-29200, |  |  | Done
NEW-0030 |  |  |  |  | NA | No
NEW-0032 |  |  |  |  | Yes | Yes
NEW-0033 |  |  |  |  | No | No
NEW-0043 |  |  |  |  | Yes | Yes
NEW-0044 |  |  |  |  | Yes | Yes
NEW-0047 |  |  |  |  | Yes | Yes
NEW-0048 |  |  |  |  | Yes | Yes
NEW-0049 |  |  |  |  | Yes | Yes
NEW-0050 |  |  |  |  | Yes | Yes
NEW-0051 |  |  |  |  | Yes | Yes
NEW-0053 |  |  |  |  | Yes | Yes
NEW-0055 |  |  |  |  | Yes | Yes
NEW-0057 |  |  |  |  | NA | NA
NEW-0058 |  |  |  |  | NA | Yes
NEW-0060 |  |  |  |  | NA | NA
NEW-0061 |  |  |  |  | NA | NA
NEW-0063 |  |  |  |  | Yes | Yes
NEW-0064 |  |  |  |  | NA | NA
NEW-0065 |  |  |  |  | NA | NA
NEW-0066 |  |  |  |  | No | No |  |  |  |  | Updates to Booking Event (DTS) | https://smartship.atlassian.net/browse/DTTP25-41759
NEW-0067 |  |  |  |  | Yes | No
NEW-0068 |  |  |  |  | No | No
NEW-0071 |  |  |  |  | NA | NA
NEW-0072 |  |  |  |  | No | No
NEW-0073 |  |  |  |  | No | No
NEW-0074 |  |  |  |  | No | No
NEW-0075 |  |  |  |  | Yes | No
NEW-0076 |  |  |  |  | Yes | No
NEW-0077 |  |  |  |  | NA | NA
NEW-0078 |  |  |  |  | NA | NA
NEW-0080 |  |  |  |  | NA | NA
NEW-0084 |  |  |  |  | No | No
NEW-0085 |  |  |  |  | No | No
NEW-0086 |  |  |  |  | No | No
NEW-0087 |  |  |  |  | No | No
NEW-0090 |  |  |  |  | Yes | Yes |  |  |  |  | --
NEW-0093 |  |  |  |  | Yes | Yes |  |  |  |  | --
NEW-0094 |  |  |  |  | Yes | Yes |  |  |  |  | --
NEW-0099 |  |  |  |  | Yes | Yes |  |  |  |  | --
NEW-0100 |  |  |  |  | Yes | Yes |  |  |  |  | S008.2v2 multiple cases | https://smartship.atlassian.net/browse/MDTTPU-6616
NEW-0103 |  |  |  |  | Yes | Yes |  |  |  |  | --
NEW-0104 |  |  |  |  | Yes | Yes |  |  |  |  | S008.2v2 multiple cases
NEW-0105 |  |  |  |  | Yes | Yes |  |  |  |  | --
NEW-0108 |  |  |  |  | Yes | Yes |  |  |  |  | --
NEW-0109 |  |  |  |  | Yes | Yes |  |  |  |  | CAI021 - new deletion of web account
NEW-0111 |  |  |  |  | Yes | Yes |  |  |  |  | updateBookingOpportunityID | https://smartship.atlassian.net/browse/MDTTPU-2414 |  | https://smartship.atlassian.net/browse/MDTTPU-498
NEW-0112 |  |  |  |  | Yes | Yes |  |  |  |  | add fields to quote object | https://smartship.atlassian.net/browse/MDTTPU-5053
NEW-0113 |  |  |  |  | Yes | Yes |  |  |  |  | AZF003
NEW-0120 |  |  |  |  | Yes | Yes |  |  |  |  | Group id/ Representative code field in S008 | https://smartship.atlassian.net/browse/MDTTPU-1668 |  | https://smartship.atlassian.net/browse/MB-6864
NEW-0121 |  |  |  |  | Yes | Yes |  |  |  |  | DTS to add group type in booking event | https://smartship.atlassian.net/browse/MDTTPU-2419
NEW-0122 |  |  |  |  | Yes | Yes |  |  |  |  | Update to R037 | https://smartship.atlassian.net/browse/MDTTPU-3614
NEW-0123 |  |  |  |  | Yes | Yes
NEW-0127 |  |  |  |  | Yes | Yes
NEW-0131 |  |  |  |  | Yes | Yes |  |  |  |  | AZF005
NEW-0133 |  |  |  |  | Yes | Yes | [7 empty] | https://smartship.atlassian.net/browse/DTTP25-29470
NEW-0135 |  |  |  |  | Yes | Yes | [7 empty] | https://smartship.atlassian.net/browse/DTTP25-33851
NEW-0136 |  |  |  |  | Yes | Yes | [7 empty] | https://smartship.atlassian.net/browse/DTTP25-33855
NEW-0137 |  |  |  |  | Yes | Yes | [7 empty] | https://smartship.atlassian.net/browse/DTTP25-33849
NEW-0138 |  |  |  |  | Yes | Yes | [7 empty] | https://smartship.atlassian.net/browse/DTTP25-33850
NEW-0139 |  |  |  |  | Yes | Yes | [7 empty] | https://smartship.atlassian.net/browse/DTTP25-33852
NEW-0142 |  |  |  |  | Yes | Yes | [7 empty] | https://smartship.atlassian.net/browse/DTTP25-6654
NEW-0143 |  |  |  |  | Yes | Yes | [7 empty] | https://smartship.atlassian.net/browse/DTTP25-32873
NEW-0146 |  |  |  |  | Yes | Yes
NEW-0148 |  |  |  |  | Yes | Yes |  |  |  |  | https://smartship.atlassian.net/browse/DTTP25-37049
NEW-0150 |  |  |  |  | Yes | Yes
NEW-0151 |  |  |  |  | Yes | Yes
NEW-0153 |  |  |  |  | Yes | Yes
NEW-0187 |  |  |  |  | Yes | Yes
NEW-0188 |  |  |  |  | Yes | Yes
NEW-0190 |  |  |  |  | Yes | Yes
NEW-0192 |  |  |  |  | Yes | Yes
NEW-0219 |  |  |  |  | Yes | Yes
NEW-0228 |  |  |  |  | Yes | Yes
NEW-0233 |  |  |  |  | Yes | Yes
NEW-0234 |  |  |  |  | Yes | Yes
NEW-0235 |  |  |  |  | Yes | Yes
NEW-0236 |  |  |  |  | Yes | Yes
NEW-0237 |  |  |  |  | Yes | Yes
NEW-0238 |  |  |  |  | Yes | Yes
NEW-0239 |  |  |  |  | Yes | Yes
NEW-0240 |  |  |  |  | Yes | Yes
NEW-0241 |  |  |  |  | Yes | Yes
NEW-0242 |  |  |  |  | Yes | Yes
NEW-0243 |  |  |  |  | Yes | Yes
NEW-0245 |  |  |  |  | Yes | Yes
NEW-0246 |  |  |  |  | Yes | Yes
NEW-0247 |  |  |  |  | Yes | Yes
NEW-0248 |  |  |  |  | Yes | Yes
NEW-0249 |  |  |  |  | Yes | Yes
NEW-0250 |  |  |  |  | Yes | Yes
NEW-0251 |  |  |  |  | Yes | Yes
NEW-0252 |  |  |  |  | Yes | Yes
NEW-0253 |  |  |  |  | Yes | Yes
NEW-0256 |  |  |  |  | Yes | Yes
NEW-0257 |  |  |  |  | Yes | Yes
NEW-0260 |  |  |  |  | Yes | Yes
NEW-0261 |  |  |  |  | Yes | Yes
NEW-0262 |  |  |  |  | Yes | Yes
NEW-0263 |  |  |  |  | Yes | Yes
NEW-0264 |  |  |  |  | Yes | Yes
NEW-0265 |  |  |  |  | Yes | Yes
NEW-0266 |  |  |  |  | Yes | Yes
NEW-0267 |  |  |  |  | Yes | Yes
NEW-0268 |  |  |  |  | Yes | Yes
NEW-0269 |  |  |  |  | Yes | Yes
NEW-0270 |  |  |  |  | No | No
NEW-0271 |  |  |  |  | Yes | Yes
NEW-0272 |  |  |  |  | Yes | Yes
NEW-0274 |  |  |  |  | No | No
NEW-0275 |  |  |  |  | NA | NA
NEW-0282 |  |  |  |  | Yes | Yes
NEW-0283 |  |  |  |  | Yes | Yes
NEW-0284 |  |  |  |  | No | No
NEW-0285 |  |  |  |  | Yes | Yes
NEW-0286 |  |  |  |  | Yes | Yes
NEW-0287 |  |  |  |  | Yes | Yes
NEW-0288 |  |  |  |  | No | No
NEW-0289 |  |  |  |  | Yes | Yes
NEW-0290 |  |  |  |  | No | No
NEW-0291 |  |  |  |  | Yes | Yes
NEW-0292 |  |  |  |  | Yes | Yes
NEW-0293 |  |  |  |  | Yes | Yes
NEW-0294 |  |  |  |  | Yes | Yes
NEW-0295 |  |  |  |  | Yes | Yes
NEW-0296 |  |  |  |  | Yes | Yes
NEW-0298 |  |  |  |  | Yes | Yes
NEW-0299 |  |  |  |  | No | No
NEW-0300 |  |  |  |  | Yes | Yes
NEW-0303 |  |  |  |  | Yes | Yes
NEW-0304 |  |  |  |  | Yes | Yes
NEW-0305 |  |  |  |  | Yes | Yes
NEW-0306 |  |  |  |  | Yes | Yes
NEW-0307 |  |  |  |  | Yes | Yes
NEW-0308 |  |  |  |  | Yes | Yes
NEW-0309 |  |  |  |  | Yes | Yes
NEW-0310 |  |  |  |  | Yes | Yes
NEW-0312 |  |  |  |  | Yes | Yes
NEW-0313 |  |  |  |  | Yes | Yes
NEW-0315 |  |  |  |  | No | No
NEW-0316 |  |  |  |  | Yes | No
NEW-0319 |  |  |  |  | Yes | Yes
NEW-0322 |  |  |  |  | No | No
NEW-0324 |  |  |  |  | No | No
NEW-0329 |  |  |  |  | Yes | Yes
NEW-0330 |  |  |  |  | Yes | Yes
NEW-0331 |  |  |  |  | Yes | Yes
NEW-0336 |  |  |  |  | Yes | Yes
NEW-0337 |  |  |  |  | Yes | Yes
NEW-0338 |  |  |  |  | Yes | Yes
NEW-0339 |  |  |  |  | Yes | Yes
NEW-0341 |  |  |  |  | Yes | Yes
NEW-0342 |  |  |  |  | Yes | Yes
NEW-0343 |  |  |  |  | No | No
NEW-0344 |  |  |  |  | No | No
NEW-0345 |  |  |  |  | No | No
NEW-0346 |  |  |  |  | No | No
NEW-0350 |  |  |  |  | Yes | Yes
NEW-0351 |  |  |  |  | Yes | Yes
NEW-0352 |  |  |  |  | Yes | Yes
NEW-0356 |  |  |  |  | No | No
NEW-0357 |  |  |  |  | Yes | Yes
NEW-0358 |  |  |  |  | No | No
NEW-0359 |  |  |  |  | Yes | Yes |  | DONE
NEW-0360 |  |  |  |  | No | No
NEW-0361 |  |  |  |  | No | No
NEW-0362 |  |  |  |  | No | No
NEW-0363 |  |  |  |  | No | No
NEW-0364 |  |  |  |  | No | No
NEW-0366 |  |  |  |  | No | No
NEW-0367 |  |  |  |  | No | No
NEW-0368 |  |  |  |  | Yes | Yes
NEW-0370 |  |  |  |  | No | No
NEW-0371 |  |  |  |  | No | No
NEW-0372 |  |  |  |  | Yes | Yes
NEW-0373 |  |  |  |  | No | No
NEW-0374 |  |  |  |  | Yes | Yes
NEW-0375 |  |  |  |  | No | No
NEW-0376 |  |  |  |  | No | No
NEW-0377 |  |  |  |  | No | No
NEW-0379 |  |  |  |  | Yes | Yes
NEW-0380 |  |  |  |  | Yes | Yes
NEW-0381 |  |  |  |  | Yes | Yes
NEW-0382 |  |  |  |  | Yes | Yes
NEW-0383 |  |  |  |  | Yes | Yes
NEW-0384 |  |  |  |  | Yes | Yes
NEW-0386 |  |  |  |  | Yes | Yes
NEW-0387 |  |  |  |  | Yes | Yes
NEW-0388 |  |  |  |  | Yes | Yes
NEW-0389 |  |  |  |  | NA | NA
NEW-0390 |  |  |  |  | Yes | Yes
NEW-0391 |  |  |  |  | Yes | Yes
NEW-0392 |  |  |  |  | Yes | Yes
NEW-0395 |  |  |  |  | No | No
NEW-0397 |  |  |  |  | No | No
NEW-0398 |  |  |  |  | No | No
NEW-0399 |  |  |  |  | No | No
NEW-0400 |  |  |  |  | No | No
NEW-0401 |  |  |  |  | No | No
NEW-0402 |  |  |  |  | No | No
NEW-0403 |  |  |  |  | No | No
NEW-0404 |  |  |  |  | No | No
NEW-0042 |  |  |  |  | Yes | Yes
NEW-0405 |  |  |  |  | No | No
NEW-0416 |  |  |  |  | Yes | Yes
NEW-0417 |  |  |  |  | Yes | Yes
NEW-0418 |  |  |  |  | Yes | Yes
NEW-0419 |  |  |  |  | Yes | Yes
NEW-0420 |  |  |  |  | Yes | Yes
NEW-0421 |  |  |  |  | Yes | Yes
NEW-0422 |  |  |  |  | Yes | Yes
NEW-0423 |  |  |  |  | Yes | Yes
NEW-0406 |  |  |  |  | Yes | Yes
NEW-0407 |  |  |  |  | No | No
NEW-0408 |  |  |  |  | Yes | No
NEW-0409 |  |  |  |  | Yes | No
NEW-0410 |  |  |  |  | Yes | No
NEW-0411 |  |  |  |  | NA | NA
NEW-0412 |  |  |  |  | NA | NA
NEW-0413 |  |  |  |  | No | No
NEW-0414 |  |  |  |  | No | No
NEW-0415 |  |  |  |  | No | No
NEW-0424 |  |  |  |  | Yes | Yes
NEW-0425 |  |  |  |  | Yes | Yes
NEW-0426 |  |  |  |  | Yes | Yes
NEW-0427 |  |  |  |  | Yes | Yes
NEW-0428 |  |  |  |  | Yes | Yes

## Sprint Planning
Requirement ID | Requirement Name | Stream | Priority | Status | Sprint | HLE | Sort Key | Total HLE by Sprint
NEW-0001 |  |  |  |  | Sprint 12 |  |  | Sprint | Total HLE
NEW-0002 |  |  |  |  | To Plan |  |  | Sprint 1
NEW-0003 |  |  |  |  | Sprint 12 |  |  | Sprint 2
NEW-0005 |  |  |  |  | To Plan |  |  | Sprint 3
NEW-0006 |  |  |  |  | To Plan |  |  | Sprint 4
NEW-0007 |  |  |  |  | To Plan |  |  | Sprint 5
NEW-0011 |  |  |  |  | To Plan |  |  | Sprint 6
NEW-0012 |  |  |  |  | Sprint 8 |  |  | Sprint 7
NEW-0015 |  |  |  |  | Sprint 8 |  |  | Sprint 8
NEW-0016 |  |  |  |  | To Plan |  |  | Sprint 9
NEW-0017 |  |  |  |  | To Plan |  |  | Sprint 10
NEW-0018 |  |  |  |  | To Plan |  |  | Sprint 11
NEW-0020 |  |  |  |  | To Plan |  |  | Sprint 12
NEW-0022 |  |  |  |  | To Plan |  |  | Sprint 13
NEW-0029 |  |  |  |  | Sprint 12 |  |  | Sprint 14
NEW-0030 |  |  |  |  | Sprint 12 |  |  | Sprint 15
NEW-0032 |  |  |  |  | Sprint 9 |  |  | Sprint 16
NEW-0033 |  |  |  |  | To Plan
NEW-0043 |  |  |  |  | Sprint 8
NEW-0044 |  |  |  |  | Sprint 8
NEW-0047 |  |  |  |  | Sprint 9
NEW-0048 |  |  |  |  | Sprint 9
NEW-0049 |  |  |  |  | Sprint 9
NEW-0050 |  |  |  |  | Sprint 9
NEW-0051 |  |  |  |  | Sprint 9
NEW-0053 |  |  |  |  | Sprint 9
NEW-0055 |  |  |  |  | Sprint 9
NEW-0057 |  |  |  |  | Sprint 10
NEW-0058 |  |  |  |  | Sprint 10
NEW-0060 |  |  |  |  | Sprint 10
NEW-0061 |  |  |  |  | Sprint 10
NEW-0063 |  |  |  |  | Sprint 7
NEW-0064 |  |  |  |  | Sprint 11
NEW-0065 |  |  |  |  | Sprint 11
NEW-0066 |  |  |  |  | Sprint 12
NEW-0067 |  |  |  |  | Sprint 12
NEW-0068 |  |  |  |  | To Plan
NEW-0071 |  |  |  |  | Sprint 10
NEW-0072 |  |  |  |  | To Plan
NEW-0073 |  |  |  |  | To Plan
NEW-0074 |  |  |  |  | To Plan
NEW-0075 |  |  |  |  | Sprint 11
NEW-0076 |  |  |  |  | Sprint 11
NEW-0077 |  |  |  |  | Sprint 11
NEW-0078 |  |  |  |  | Sprint 11
NEW-0080 |  |  |  |  | Sprint 12
NEW-0084 |  |  |  |  | To Plan
NEW-0085 |  |  |  |  | Sprint 12
NEW-0086 |  |  |  |  | Sprint 12
NEW-0087 |  |  |  |  | Sprint 12
NEW-0090 |  |  |  |  | Sprint 1
NEW-0093 |  |  |  |  | Sprint 2
NEW-0094 |  |  |  |  | Sprint 2
NEW-0099 |  |  |  |  | Sprint 3
NEW-0100 |  |  |  |  | Sprint 6
NEW-0103 |  |  |  |  | Sprint 6
NEW-0104 |  |  |  |  | Sprint 6
NEW-0105 |  |  |  |  | Sprint 6
NEW-0108 |  |  |  |  | Sprint 5
NEW-0109 |  |  |  |  | Sprint 5
NEW-0111 |  |  |  |  | Sprint 6
NEW-0112 |  |  |  |  | Sprint 7
NEW-0113 |  |  |  |  | Sprint 7
NEW-0120 |  |  |  |  | Sprint 7
NEW-0121 |  |  |  |  | Sprint 7
NEW-0122 |  |  |  |  | Sprint 7
NEW-0123 |  |  |  |  | Sprint 4
NEW-0127 |  |  |  |  | Sprint 6
NEW-0131 |  |  |  |  | Sprint 6
NEW-0133 |  |  |  |  | Sprint 3
NEW-0135 |  |  |  |  | Sprint 5
NEW-0136 |  |  |  |  | Sprint 5
NEW-0137 |  |  |  |  | Sprint 5
NEW-0138 |  |  |  |  | Sprint 5
NEW-0139 |  |  |  |  | Sprint 5
NEW-0142 |  |  |  |  | Sprint 5
NEW-0143 |  |  |  |  | Sprint 6
NEW-0146 |  |  |  |  | Sprint 6
NEW-0148 |  |  |  |  | Sprint 6
NEW-0150 |  |  |  |  | Sprint 6
NEW-0151 |  |  |  |  | Sprint 7
NEW-0153 |  |  |  |  | Sprint 5
NEW-0187 |  |  |  |  | Sprint 5
NEW-0188 |  |  |  |  | Sprint 5
NEW-0190 |  |  |  |  | Sprint 5
NEW-0192 |  |  |  |  | Sprint 5
NEW-0219 |  |  |  |  | Sprint 7
NEW-0228 |  |  |  |  | Sprint 7
NEW-0233 |  |  |  |  | Sprint 7
NEW-0234 |  |  |  |  | Sprint 7
NEW-0235 |  |  |  |  | Sprint 1
NEW-0236 |  |  |  |  | Sprint 2
NEW-0237 |  |  |  |  | Sprint 1
NEW-0238 |  |  |  |  | Sprint 1
NEW-0239 |  |  |  |  | Sprint 3
NEW-0240 |  |  |  |  | Sprint 6
NEW-0241 |  |  |  |  | Sprint 2
NEW-0242 |  |  |  |  | Sprint 7
NEW-0243 |  |  |  |  | Sprint 6
NEW-0245 |  |  |  |  | Sprint 2
NEW-0246 |  |  |  |  | Sprint 6
NEW-0247 |  |  |  |  | Sprint 7
NEW-0248 |  |  |  |  | Sprint 7
NEW-0249 |  |  |  |  | Sprint 4
NEW-0250 |  |  |  |  | Sprint 4
NEW-0251 |  |  |  |  | Sprint 4
NEW-0252 |  |  |  |  | Sprint 4
NEW-0253 |  |  |  |  | Sprint 6
NEW-0256 |  |  |  |  | Sprint 5
NEW-0257 |  |  |  |  | Sprint 6
NEW-0260 |  |  |  |  | Sprint 4
NEW-0261 |  |  |  |  | Sprint 4
NEW-0262 |  |  |  |  | Sprint 4
NEW-0263 |  |  |  |  | Sprint 8
NEW-0264 |  |  |  |  | Sprint 8
NEW-0265
NEW-0266
NEW-0267 |  |  |  |  | Sprint 7
NEW-0268 |  |  |  |  | Sprint 6
NEW-0269 |  |  |  |  | Sprint 7
NEW-0270 |  |  |  |  | To Plan
NEW-0271 |  |  |  |  | Sprint 7
NEW-0272 |  |  |  |  | Sprint 8
NEW-0274 |  |  |  |  | To Plan
NEW-0275 |  |  |  |  | Sprint 10
NEW-0282 |  |  |  |  | Sprint 3
NEW-0283 |  |  |  |  | Sprint 5
NEW-0284 |  |  |  |  | To Plan
NEW-0285 |  |  |  |  | Sprint 2
NEW-0286 |  |  |  |  | Sprint 3
NEW-0287 |  |  |  |  | Sprint 5
NEW-0288 |  |  |  |  | To Plan
NEW-0289 |  |  |  |  | Sprint 5
NEW-0290 |  |  |  |  | To Plan
NEW-0291 |  |  |  |  | Sprint 6
NEW-0292 |  |  |  |  | Sprint 8
NEW-0293 |  |  |  |  | Sprint 8
NEW-0294 |  |  |  |  | Sprint 6
NEW-0295 |  |  |  |  | Sprint 5
NEW-0296 |  |  |  |  | Sprint 5
NEW-0298 |  |  |  |  | Sprint 5
NEW-0299 |  |  |  |  | To Plan
NEW-0300 |  |  |  |  | Sprint 5
NEW-0303 |  |  |  |  | Sprint 6
NEW-0304 |  |  |  |  | Sprint 7
NEW-0305 |  |  |  |  | Sprint 6
NEW-0306 |  |  |  |  | Sprint 4
NEW-0307 |  |  |  |  | Sprint 6
NEW-0308 |  |  |  |  | Sprint 4
NEW-0309 |  |  |  |  | Sprint 4
NEW-0310 |  |  |  |  | Sprint 7
NEW-0312 |  |  |  |  | Sprint 7
NEW-0313 |  |  |  |  | Sprint 8
NEW-0315 |  |  |  |  | To Plan
NEW-0316 |  |  |  |  | Sprint 12
NEW-0319 |  |  |  |  | Sprint 6
NEW-0322 |  |  |  |  | To Plan
NEW-0324 |  |  |  |  | To Plan
NEW-0329 |  |  |  |  | Sprint 1
NEW-0330 |  |  |  |  | Sprint 2
NEW-0331 |  |  |  |  | Sprint 2
NEW-0336 |  |  |  |  | Sprint 1
NEW-0337 |  |  |  |  | Sprint 3
NEW-0338 |  |  |  |  | Sprint 3
NEW-0339 |  |  |  |  | Sprint 4
NEW-0341 |  |  |  |  | Sprint 8
NEW-0342 |  |  |  |  | Sprint 8
NEW-0343 |  |  |  |  | To Plan
NEW-0344 |  |  |  |  | To Plan
NEW-0345 |  |  |  |  | To Plan
NEW-0346 |  |  |  |  | To Plan
NEW-0350 |  |  |  |  | Sprint 3
NEW-0351 |  |  |  |  | Sprint 3
NEW-0352 |  |  |  |  | Sprint 6
NEW-0356 |  |  |  |  | To Plan
NEW-0357 |  |  |  |  | Sprint 6
NEW-0358 |  |  |  |  | To Plan
NEW-0359 |  |  |  | DONE | Sprint 9
NEW-0360 |  |  |  |  | To Plan
NEW-0361 |  |  |  |  | To Plan
NEW-0362 |  |  |  |  | To Plan
NEW-0363 |  |  |  |  | To Plan
NEW-0364 |  |  |  |  | To Plan
NEW-0366 |  |  |  |  | To Plan
NEW-0367 |  |  |  |  | To Plan
NEW-0368 |  |  |  |  | Sprint 10
NEW-0370 |  |  |  | NEW | To Plan
NEW-0371 |  |  |  |  | To Plan
NEW-0372 |  |  |  |  | Sprint 1
NEW-0373 |  |  |  |  | To Plan
NEW-0374 |  |  |  |  | Sprint 2
NEW-0375 |  |  |  |  | To Plan
NEW-0376 |  |  |  |  | To Plan
NEW-0377 |  |  |  |  | To Plan
NEW-0379 |  |  |  |  | Sprint 1
NEW-0380 |  |  |  |  | Sprint 8
NEW-0381 |  |  |  |  | Sprint 1
NEW-0382 |  |  |  |  | Sprint 4
NEW-0383 |  |  |  |  | Sprint 2
NEW-0384
NEW-0386 |  |  |  |  | Sprint 5
NEW-0387 |  |  |  |  | Sprint 6
NEW-0388 |  |  |  |  | Sprint 7
NEW-0389 |  |  |  |  | Sprint 10
NEW-0390 |  |  |  |  | Sprint 7
NEW-0391 |  |  |  |  | Sprint 1
NEW-0392 |  |  |  |  | Sprint 9
NEW-0395 |  |  |  |  | To Plan
NEW-0397 |  |  |  |  | To Plan
NEW-0398 |  |  |  |  | To Plan
NEW-0399 |  |  |  |  | To Plan
NEW-0400 |  |  |  |  | To Plan
NEW-0401 |  |  |  |  | To Plan
NEW-0402 |  |  |  |  | To Plan
NEW-0403 |  |  |  |  | To Plan
NEW-0404 |  |  |  |  | To Plan
NEW-0042 |  |  |  |  | Sprint 8
NEW-0405 |  |  |  |  | To Plan
NEW-0408 |  |  |  |  | Sprint 10
NEW-0409 |  |  |  |  | Sprint 11
NEW-0410 |  |  |  |  | Sprint 11
NEW-0411 |  |  |  |  | Sprint 10
NEW-0412 |  |  |  |  | Sprint 10
NEW-0416 |  |  |  |  | Sprint 9
NEW-0417 |  |  |  |  | Sprint 8
NEW-0418 |  |  |  |  | Sprint 8
NEW-0419 |  |  |  |  | Sprint 3
NEW-0420 |  |  |  |  | Sprint 7
NEW-0421 |  |  |  |  | Sprint 7
NEW-0422 |  |  |  |  | Sprint 7
NEW-0423 |  |  |  |  | Sprint 3
NEW-0406 |  |  |  |  | Sprint 9
NEW-0407 |  |  |  |  | To Plan
NEW-0413 |  |  |  |  | To Plan
NEW-0414 |  |  |  |  | To Plan
NEW-0415 |  |  |  |  | To Plan
NEW-0424 |  |  |  |  | Sprint 3
NEW-0425 |  |  |  |  | Sprint 3
NEW-0426 |  |  |  |  | Sprint 9
NEW-0427 |  |  |  |  | Sprint 9
NEW-0428 |  |  |  |  | Sprint 9

## Roadmap
Roadmap — Total HLE by Stream and Sprint (all team, view only) | [17 empty] | Gantt Order (helper)
Stream | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16 | Total
US
MyMSC
Growth
MVP Rollout
Cross
PI11
Backlog
Tech Enhancements
PP
HR
PI9
PI10
Total
6-Month Look-ahead Gantt (Sprint 10 - Sprint 16, Aug 3 - Dec 24 2026) -- limited to sprints already defined on the Lists tab; extend the Sprint->Quarter mapping there to push this further into 2027.
Stream | Task |  | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14 | Sprint 15 | Sprint 16

## Release
Requirement ID | Requirement Name | Stream | Sprint | Status | Priority | Release | HLE | Breakdown by Release
NEW-0090 | [5 empty] | Release 18 |  | Release | Item Count | Total HLE | Production Date | Cutoff Date | Status | Service Now CR ID
NEW-0235 | [5 empty] | Release 5B |  | Release 5
NEW-0237 | [5 empty] | Release 19 |  | Release 5A
NEW-0238 | [5 empty] | Release 19 |  | Release 5B
NEW-0329 | [5 empty] | Release 5A |  | Release 5B (Hotfix)
NEW-0336 | [5 empty] | Release 7 |  | Release 5C
NEW-0372 | [7 empty] | Release 6
NEW-0379 | [7 empty] | Release 7
NEW-0381 | [7 empty] | Release 7A (Hotfix)
NEW-0391 | [7 empty] | Release 7B (Hotfix)
NEW-0093 | [5 empty] | Release 19 |  | Release 8
NEW-0094 | [5 empty] | Release 19 |  | Release 9 |  |  | 2026-04-07 |  | Completed
NEW-0236 | [7 empty] | Release 10 |  |  | 2026-04-16 |  | Completed
NEW-0241 | [5 empty] | Release 19 |  | Release 10A
NEW-0245 | [5 empty] | Release 19 |  | Release 10B (Hotfix)
NEW-0285 | [5 empty] | Release 12 |  | Release 10C (Hotfix)
NEW-0330 | [7 empty] | Release 11 |  |  | 2026-05-14 |  | Completed | CHG0068937
NEW-0331 | [7 empty] | Release 11A
NEW-0337 | [7 empty] | Release 12 |  |  | 2026-06-04 |  | Completed | CHG0069184
NEW-0374 | [7 empty] | Release 13 |  |  |  |  | Completed | CHG0069187
NEW-0380 | [5 empty] | Release 17 |  | Release 13A (Hotfix)
NEW-0383 | [5 empty] | Release 15 |  | Release 13B (Hotfix)
NEW-0099 | [5 empty] | Release 18 |  | Release 13C (Hotfix)
NEW-0133 | [5 empty] | Release 12 |  | Release 14
NEW-0239 | [5 empty] | Release 18 |  | Release 14A
NEW-0282 | [7 empty] | Release 15 |  |  | 2026-07-14 |  | Completed | CHG0070359
NEW-0286 | [7 empty] | Release 15A
NEW-0338 | [7 empty] | Release 15B
NEW-0350 | [5 empty] | Release 9 |  | Release 15C |  |  | 2026-07-16 |  | Completed | CHG0070881
NEW-0351 | [7 empty] | Release 16 |  |  | 2025-07-23 |  | Completed | CHG0070954
NEW-0123 | [5 empty] | Release 19 |  | Release 17 |  |  |  |  | Planned | CHG0071104
NEW-0249 | [5 empty] | Release 19 |  | Release 19 |  |  | 2026-09-01 |  | Planned | CHG0071296
NEW-0250 | [5 empty] | Release 19 |  | (Unassigned)
NEW-0251 | [5 empty] | Release 19
NEW-0252 | [5 empty] | Release 19
NEW-0260 | [5 empty] | Release 19
NEW-0261 | [5 empty] | Release 19
NEW-0262 | [5 empty] | Release 18
NEW-0306
NEW-0308 | [5 empty] | Release 12
NEW-0309
NEW-0339 | [5 empty] | Release 10
NEW-0382
NEW-0108 | [5 empty] | Release 18
NEW-0109 | [5 empty] | Release 19
NEW-0135 | [5 empty] | Release 12
NEW-0136 | [5 empty] | Release 12
NEW-0137 | [5 empty] | Release 12
NEW-0138 | [5 empty] | Release 12
NEW-0139 | [5 empty] | Release 12
NEW-0142 | [5 empty] | Release 12
NEW-0153 | [5 empty] | Release 19
NEW-0187 | [5 empty] | Release 11
NEW-0188
NEW-0190 | [5 empty] | Release 19
NEW-0192
NEW-0256 | [5 empty] | Release 19
NEW-0283
NEW-0287
NEW-0289
NEW-0295
NEW-0296
NEW-0298
NEW-0300 | [5 empty] | Release 12
NEW-0386
NEW-0100 | [5 empty] | Release 19
NEW-0103 | [5 empty] | Release 19
NEW-0104 | [5 empty] | Release 18
NEW-0105 | [5 empty] | Release 18
NEW-0111 | [5 empty] | Release 18
NEW-0127 | [5 empty] | Release 13
NEW-0131 | [5 empty] | Release 15
NEW-0143 | [5 empty] | Release 13
NEW-0146 | [5 empty] | Release 13
NEW-0148 | [5 empty] | Release 13
NEW-0150
NEW-0240 | [5 empty] | Release 19
NEW-0243 | [5 empty] | Release 18
NEW-0246 | [5 empty] | Release 18
NEW-0253 | [5 empty] | Release 18
NEW-0257 | [5 empty] | Release 18
NEW-0268 | [5 empty] | Release 19
NEW-0291 | [5 empty] | Release 13
NEW-0294
NEW-0303
NEW-0305 | [5 empty] | Release 13
NEW-0307 | [5 empty] | Release 13
NEW-0319 | [5 empty] | Release 13
NEW-0352 | [5 empty] | Release 15
NEW-0357 | [5 empty] | Release 13
NEW-0387 | [5 empty] | Release 13
NEW-0112 | [5 empty] | Release 18
NEW-0113 | [5 empty] | Release 18
NEW-0120 | [5 empty] | Release 18
NEW-0121 | [5 empty] | Release 18
NEW-0122 | [5 empty] | Release 19
NEW-0151
NEW-0219 | [5 empty] | Release 18
NEW-0228 | [5 empty] | Release 13
NEW-0233 | [5 empty] | Release 15
NEW-0234
NEW-0242 | [5 empty] | Release 18
NEW-0247 | [5 empty] | Release 18
NEW-0248 | [5 empty] | Release 18
NEW-0267
NEW-0269 | [5 empty] | Release 18
NEW-0271 | [5 empty] | Release 18
NEW-0304 | [5 empty] | Release 13
NEW-0310
NEW-0312 | [5 empty] | Release 15
NEW-0388 | [5 empty] | Release 15C
NEW-0390 | [5 empty] | Release 15C
NEW-0012 | [5 empty] | Release 18
NEW-0015 | [5 empty] | Release 18
NEW-0042 | [5 empty] | Release 15
NEW-0043
NEW-0044
NEW-0263 | [5 empty] | Release 18
NEW-0264 | [5 empty] | Release 18
NEW-0272 | [5 empty] | Release 18
NEW-0292
NEW-0293 | [5 empty] | Release 16
NEW-0313 | [5 empty] | Release 15
NEW-0341 | [5 empty] | Release 15C
NEW-0342
NEW-0047 | [5 empty] | Release 18
NEW-0048 | [5 empty] | Release 18
NEW-0049 | [5 empty] | Release 18
NEW-0050 | [5 empty] | Release 18
NEW-0051 | [5 empty] | Release 18
NEW-0053 | [5 empty] | Release 18
NEW-0055 | [5 empty] | Release 18
NEW-0359 |  |  |  | DONE |  | Release 18
NEW-0389
NEW-0392
NEW-0057 | [5 empty] | Release 19
NEW-0058 | [5 empty] | Release 19
NEW-0060 | [5 empty] | Release 19
NEW-0061 | [5 empty] | Release 19
NEW-0063 | [5 empty] | Release 15
NEW-0064
NEW-0065
NEW-0066
NEW-0067
NEW-0068
NEW-0071 | [5 empty] | Release 19
NEW-0275 | [5 empty] | Release 19
NEW-0290
NEW-0368 | [5 empty] | Release 19
NEW-0072
NEW-0073
NEW-0074
NEW-0075
NEW-0076
NEW-0077
NEW-0078
NEW-0288
NEW-0080
NEW-0084
NEW-0085
NEW-0086
NEW-0087
NEW-0001
NEW-0003
NEW-0029
NEW-0030
NEW-0032
NEW-0416 | [5 empty] | Release 18
NEW-0417 | [5 empty] | Release 18
NEW-0418 | [5 empty] | Release 16
NEW-0419 | [5 empty] | Release 15
NEW-0420 | [5 empty] | Release 15
NEW-0421 | [5 empty] | Release 15
NEW-0422 | [5 empty] | Release 15
NEW-0423 | [5 empty] | Release 9
NEW-0408
NEW-0409
NEW-0410
NEW-0411
NEW-0412
NEW-0424
NEW-0425
NEW-0426
NEW-0427
NEW-0428

## Q1 Backlog Report 2026
Requirement ID | Requirement Name | Type | Stream | Stream Owner | Status | Jira Key | Jira Link | Priority | Sprint | Release | HLE

## Q2 Backlog Report 2026
Requirement ID | Requirement Name | Type | Stream | Stream Owner | Status | Jira Key | Jira Link | Priority | Sprint | Release | HLE

## Q3 Backlog Report 2026
Requirement ID | Requirement Name | Type | Stream | Stream Owner | Status | Jira Key | Jira Link | Priority | Sprint | Release | HLE

## Q4 Backlog Report 2026
Requirement ID | Requirement Name | Type | Stream | Stream Owner | Status | Jira Key | Jira Link | Priority | Sprint | Release | HLE

## Lists (hidden)
Type | Stream | Status | Priority | Sprint | RAML Required | Release | Assignee | Stream Owner | Sprint->Quarter (2026) | Quarter Tab | Date Range
Config | US | NEW | Critical | To Plan | Yes | Release 5 | Clare | ALL | Sprint 1 | Q1 Backlog Report 2026 | Jan 19 - Feb 6
CR | MyMSC | IN PROGRESS | High | Sprint 1 | No | Release 5A | Luke | DTS | Sprint 2 | Q1 Backlog Report 2026 | Feb 9 - Feb 27
New | Growth | DONE | Medium | Sprint 2 | TBC | Release 5B | Bipin | MA | Sprint 3 | Q1 Backlog Report 2026 | Mar 2 - Mar 20
TBC | MVP Rollout | ON HOLD | Low | Sprint 3 |  | Release 5B (Hotfix) | Remo | B2CW | Sprint 4 | Q1 Backlog Report 2026 | Mar 23 - Apr 10
Bug | Cross | NA |  | Sprint 4 |  | Release 5C |  | S&S | Sprint 5 | Q2 Backlog Report 2026 | Apr 13 - May 8
Tech Task | PI11 |  |  | Sprint 5 |  | Release 6 |  | EPAM B2C | Sprint 6 | Q2 Backlog Report 2026 | May 11 - May 29
Tech Story | Backlog |  |  | Sprint 6 |  | Release 7 |  | CHUB | Sprint 7 | Q2 Backlog Report 2026 | Jun 1 - Jun 19
| Tech Enhancements |  |  | Sprint 7 |  | Release 7A (Hotfix) |  | CRMASIS | Sprint 8 | Q2 Backlog Report 2026 | Jun 22 - Jul 10
| PP |  |  | Sprint 8 |  | Release 7B (Hotfix) |  | M4M | Sprint 9 | Q3 Backlog Report 2026 | Jul 13 - Jul 31
| HR |  |  | Sprint 9 |  | Release 8 |  |  | Sprint 10 | Q3 Backlog Report 2026 | Aug 3 - Aug 21
| PI9 |  |  | Sprint 10 |  | Release 9 |  |  | Sprint 11 | Q3 Backlog Report 2026 | Aug 24 - Sep 11
| PI10 |  |  | Sprint 11 |  | Release 10 |  |  | Sprint 12 | Q3 Backlog Report 2026 | Sep 14 - Oct 2
| M4M |  |  | Sprint 12 |  | Release 10A |  |  | Sprint 13 | Q4 Backlog Report 2026 | Oct 5 - Oct 23
|  |  |  | Sprint 13 |  | Release 10B (Hotfix) |  |  | Sprint 14 | Q4 Backlog Report 2026 | Oct 26 - Nov 13
|  |  |  | Sprint 14 |  | Release 10C (Hotfix) |  |  | Sprint 15 | Q4 Backlog Report 2026 | Nov 16 - Dec 4
|  |  |  | Sprint 15 |  | Release 11 |  |  | Sprint 16 | Q4 Backlog Report 2026 | Dec 7 - Dec 24
|  |  |  | Sprint 16 |  | Release 11A
Release 12
Release 13
Release 13A (Hotfix)
Release 13B (Hotfix)
Release 13C (Hotfix)
Release 14
Release 14A
Release 15
Release 15A
Release 15B
Release 15C
Release 16
Release 17
Release 18
Release 19